## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2023-04-18
Group Number |  | 36
Participant 1 |  | Tobias Stoderegger
Participant 2 |  | Paul Panosch
Participant 3
Participant 4
Participant 5
Mentor |  | Christian Osterbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Design für Einstellungen-Popup | 4 | 4.5 | 0.5 | x
2 | Design für Freunde-Popup entwerfen | 2 | 1.5 | -0.5 | x
3 | Backend erstellen | 2 | 1.5 | -0.5 | x
4 | Frontend erstellen | 1 | 2.5 | 1.5 | x |  | Projekt-Abhängigkeiten konfigurieren hat länger gedauert als gedacht
5 | Registrierung einbauen | 8 | 7 | -1 | x |  | Datenbank mapping ging schneller als erwartet
6 | Registrierungs-Seite erstellen | 4 | 7.5 | 3.5 |  | x | Es wurden Dinge beim Schätzen vergessen, die nicht direkt mit dem Feature zusammenhängen, jedoch gemacht werden müssen, um das Feature fertigzustellen
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 3.5 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol